## MD Consent Catch Up
Design Early Detection Tool for Diabetes Project
Intelligent Healthcare Limited
Project Lead: David Hui |  | Project Start: |  | 2020-11-01
|  | Display Week: |  | 1 |  |  | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14 | [6 empty] | 2020-12-21 | [6 empty] | 2020-12-28 | [6 empty] | 2021-01-04 | [6 empty] | 2021-01-11
 | time axis 2020-11-02 to 2021-01-17
TASK | ASSIGNED Team | Deliverables | PROGRESS | START | END | DAYS | time axis 2020-11-02 to 2021-01-17
Literature Research | Reseach
Topic selection |  | Topic | 100% | 2020-11-01 | 2020-11-05 | 5
Paper research |  | Papers | 100% | 2020-11-05 | 2020-11-23
Reading papers |  |  | 50% | 2020-11-23 | 2020-12-13 | 21
Paper evaluation |  |  | 10% | 2020-12-13 | 2020-12-17 | 5
Literature Review Rpeort write-up |  | Report | 10% | 2020-12-17 | 2020-12-24 | 8
Literature Review Rpeort submission |  | Report | 0% | 2020-12-24 | 2020-12-27 | 4
Data Preparation | Data Science
Data research |  | Dataset | 100% | 2020-11-05 | 2020-12-15 | 41
Data cleansing |  | Dataset | 0% | 2020-12-27 | 2020-12-28 | 2
Design Phase | Data Science
Gantt chart design |  | Gantt chart | 100% | 2020-11-01 | 2020-11-03 | 3
Frame & select theme |  | theme | 50% | 2020-12-27 | 2020-12-28
Product Specification design |  | product specification | 0% | 2020-12-28 | 2020-12-29
Product software architecture design |  | software architecture | 0% | 2020-12-28 | 2020-12-29 | 2
Risk Assessment on personal info protection & data security |  | plan | 0% | 2020-12-28 | 2020-12-29
Implement Phase | Data Science
Software tool & hardware methodology selection |  | software& hardware | 0% | 2020-12-28 | 2020-12-29 | 2
Software engineering methodology selection |  | method | 0% | 2020-12-28 | 2020-12-29 | 2
Data visualization |  | charts | 0% | 2020-12-29 | 2021-01-01
Machine learning model |  | model | 0% | 2020-12-29 | 2021-01-02
Tool Interface with Charts & Model |  | tool | 0% | 2020-12-29 | 2021-01-05
Test Phase | IT & Data Science
Tool testing |  | tool | 0% | 2021-01-05 | 2021-01-06
User evalution plan and method |  | plan | 0% | 2021-01-06 | 2021-01-06
Deploy Phase | IT
Upload the product prototype |  | tool | 0% | 2021-01-06 | 2021-01-07
Maintenance Phase | IT
Quality control on software development |  | plan | 0% | 2021-01-07 | 2021-01-07
Launch Phase | Marketing
Customer relationship management plan |  | plan | 0% | 2020-12-29 | 2021-01-08
Product makreting strategy |  | plan | 0% | 2020-12-29 | 2021-01-08
Project Report | Data Science
Report write-up |  | report | 0% | 2020-12-27 | 2021-01-12
Report submission |  | report | 0% | 2021-01-12 | 2021-01-14
Insert new rows ABOVE this one