## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Early Prediction Diagnostic Tool for DM Patient |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | David Hui |  |  |  |  | DATE | [6 empty] | 2020-11-01
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Literature Research (Assignment 1)
1.1 | Choose Topic |  | 2020-11-01 | 2020-11-05 | 4 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Dataset collection |  | 2020-11-05 | 2020-11-10 | 5 | 100% | bar: WEEK 2 W
1.2 | Research paper |  | 2020-11-05 | 2020-12-05 | 30 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Read paper |  | 2020-12-05 | 2020-12-13 | 8 | 50% | bar: WEEK 2 R to WEEK 3 R
1.4 | Evaluate paper |  | 2020-12-13 | 2020-12-16 | 3 | 0% | bar: WEEK 3 M to WEEK 3 R
1.5 | Write up |  | 2020-12-16 | 2020-12-23 | 7 | 0% | bar: WEEK 3 T to WEEK 3 R
1.6 | Submit report |  |  |  | 0 | 0% | bar: WEEK 3 F
2 | Product Prototype (Assignment 2)
2.1 | Dataset cleaning |  | 2020-12-28 | 29/12/20 | 2 | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 | ML algothrim (Rapidminer) |  | 29/12/20 | 30/12/20 | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | Data visualization (Tableau) |  | 30/12/20 | 31/12/20 | 0 | 0%
2.4 | Html Design (JavaScript) |  | 2021-01-01 | 2021-01-04 | 0 | 0%
3 | Report
3.1 | Write up |  | 2021-04-01 | 13/1/21 | 0 | 0%
3.2 |  |  |  |  | 0 | 0%
3.2.1 |  |  |  |  | 0 | 0%
3.2.2 |  |  |  |  | 0 | 0%
3.3 |  |  |  |  | 0 | 0%
3.3.1 |  |  |  |  | 0 | 0%
4
4.1 |  |  |  |  | 0 | 0%
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 |  |  |  |  | 0 | 0%